## Sheet1
Tasks |  | Weeks
|  | Semester 1 | [11 empty] | Exams |  |  | Semester 2
|  | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 01 | 02 | 03 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
1 | bar: Semester 1 01 to Semester 1 04
1.1 | bar: Semester 1 01 to Semester 1 03
1.2 | bar: Semester 1 03 to Semester 1 04
1.3 | bar: Semester 1 04
2 | bar: Semester 1 04 to Exams 01
2.1 | bar: Semester 1 04 to Semester 1 10
2.2 | bar: Semester 1 06 to Semester 1 08
2.3 | bar: Semester 1 08 to Semester 1 11
2.4 | bar: Semester 1 10 to Exams 01
2.5 | bar: Exams 01
3 | bar: Semester 1 08 to Exams 01
3.1 | bar: Semester 1 08 to Semester 1 12
3.2 | bar: Semester 1 11 to Exams 01
3.3 | bar: Semester 1 12 to Exams 01
3.4 | bar: Exams 01
4 | bar: Semester 1 10 to Exams 02
4.1 | bar: Semester 1 10
4.2 | bar: Semester 1 10 to Semester 1 11
4.3 | bar: Semester 1 11 to Exams 01
4.4 | bar: Exams 02
5 | bar: Semester 2 07 to Semester 2 10
5.1 | bar: Semester 2 07 to Semester 2 08
5.2 | bar: Semester 2 09 to Semester 2 10
5.3 | bar: Semester 2 10
6 | bar: Exams 01 to Semester 2 11
6.1 | bar: Exams 01 to Semester 2 01
6.2 | bar: Exams 03 to Semester 2 03
6.3 | bar: Semester 2 03 to Semester 2 09
6.4 | bar: Semester 2 04 to Semester 2 10
6.5 | bar: Semester 2 10
[29 empty] | Tasks |  | Description
Sub-tasks
[29 empty] | 1 |  | PID
[30 empty] | 1.1 | Initial research
[30 empty] | 1.2 | Write-up
[30 empty] | 1.3 | Hand-in
[29 empty] | 2 |  | Interim Report
[30 empty] | 2.1 | Further research
[30 empty] | 2.2 | Mathematical design of closed-loop loudspeaker system
[30 empty] | 2.3 | Computer simulation of design
[30 empty] | 2.4 | Report writing
[30 empty] | 2.5 | Hand-in
[29 empty] | 3 |  | 2nd marker viva
[30 empty] | 3.1 | Collation of understanding, achieved and future milestones
[30 empty] | 3.2 | Slide preparation
[30 empty] | 3.3 | Practice and preparation
[30 empty] | 3.4 | Presentation
[29 empty] | 4 |  | Public engagement video
[30 empty] | 4.1 | Target audience choice
[30 empty] | 4.2 | Storyboarding
[30 empty] | 4.3 | Filming / animating and editing
[30 empty] | 4.4 | Hand-in
[29 empty] | 5 |  | Symposium
[30 empty] | 5.1 | Adaptation of viva slides
[30 empty] | 5.2 | Practice and preparation
[30 empty] | 5.3 | Presentations
[29 empty] | 6 |  | IEEE Article
[30 empty] | 6.1 | Further research and design of loudspeaker system
[30 empty] | 6.2 | Parts purchase and build
[30 empty] | 6.3 | Troubleshooting, testing and validating
[30 empty] | 6.4 | Report writing
[30 empty] | 6.5 | Hand-in