## Sheet1
Tasks
|  | Exams |  |  | Semester 2
|  | 01 | 02 | 03 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
1
1.1
1.2
1.3
2 | bar: Exams 01
2.1
2.2
2.3
2.4 | bar: Exams 01
2.5 | bar: Exams 01
3 | bar: Exams 01
3.1
3.2 | bar: Exams 01
3.3 | bar: Exams 01
3.4 | bar: Exams 01
4 | bar: Exams 01 to Exams 02
4.1
4.2
4.3 | bar: Exams 01
4.4 | bar: Exams 02
5 | bar: Semester 2 07 to Semester 2 10
5.1 | bar: Semester 2 07 to Semester 2 08
5.2 | bar: Semester 2 09 to Semester 2 10
5.3 | bar: Semester 2 10
6
6.1 | bar: Semester 2 01 to Semester 2 02
6.2 | bar: Exams 03 to Semester 2 03
6.3 | bar: Semester 2 03 to Semester 2 09
6.4 | bar: Semester 2 04 to Semester 2 10
6.5 | bar: Semester 2 10
[17 empty] | Tasks |  | Description
Sub-tasks
[17 empty] | 1 |  | PID
[18 empty] | 1.1 | Initial research
[18 empty] | 1.2 | Write-up
[18 empty] | 1.3 | Hand-in
[17 empty] | 2 |  | Interim Report
[18 empty] | 2.1 | Further research
[18 empty] | 2.2 | Mathematical design of closed-loop loudspeaker system
[18 empty] | 2.3 | Computer simulation of design
[18 empty] | 2.4 | Report writing
[18 empty] | 2.5 | Hand-in
[17 empty] | 3 |  | 2nd marker viva
[18 empty] | 3.1 | Collation of understanding, achieved and future milestones
[18 empty] | 3.2 | Slide preparation
[18 empty] | 3.3 | Practice and preparation
[18 empty] | 3.4 | Presentation
[17 empty] | 4 |  | Public engagement video
[18 empty] | 4.1 | Target audience choice
[18 empty] | 4.2 | Storyboarding
[18 empty] | 4.3 | Filming / animating and editing
[18 empty] | 4.4 | Hand-in
[17 empty] | 5 |  | Symposium
[18 empty] | 5.1 | Adaptation of viva slides
[18 empty] | 5.2 | Practice and preparation
[18 empty] | 5.3 | Presentations
[17 empty] | 6 |  | IEEE Article
[18 empty] | 6.1 | Loudspeaker in enclosure built and tested - 'normal' measurements obtained
[18 empty] | 6.2 | Linkwitz Transform design and build on breadboard, test against normal
[18 empty] | 6.3 | Closed-loop circuit design and build on breadboard, test against normal
[18 empty] | 6.4 | Report writing
[18 empty] | 6.5 | Hand-in